Guide 2. APT Project Development

Capstone Course

1. APT Project Progress Summary

Below you will find several fields that you must complete with the requested information.

| APT project progress summary | To date we have fully completed the Planning Phase (Project Charter, approval, definition of general requirements, and team organization) and the Analysis and Design Phase (specific requirements, System Architecture Document with its class, relational, sequence, and activity diagrams, Extended Use Case Document, Mockups/Prototypes, and the SRS Proposal). We have now entered the Development Phase: the development environment was set up, the database table creation and PL/SQL query scripts were created in Supabase, and the institutional authentication and login module was completed. We are currently finishing the registration, roles, and profile management module, and starting the activities CRUD module. No adjustments have been made to the objectives or the methodology defined in the Project Charter. |
| --- | --- |
| Objectives | Not applicable: no adjustments have been made to the objectives defined in the project Charter. |
| Methodology | A Waterfall methodology with feedback will be used. Considering that the project scope is limited and no significant changes are anticipated, this approach is appropriate as it avoids incorporating the inherent complexity of agile methodologies. Continuous adjustments and constant iterations are not required, which simplifies management and fully adapts to the characteristics of the project. Another relevant aspect is the ease of tracking and control. Having clear and orderly phases makes it simpler to monitor progress, allocate resources, and meet established deadlines. This is especially important when the working team is small or lacks extensive experience in more flexible methodologies. |
| Evidence of progress | Attached are the updated Gantt Chart, the System Architecture Document (SAD) with its diagrams, the Mockups Document, the SQL scripts for table creation and database queries, and the functional authentication module. This evidence accounts for both documentation progress (architecture, design, requirements) and actual technical progress (operational database and first functional module of the system). To safeguard quality, the database design was validated against the SAD's relational model before the scripts were created, and frontend/backend development relies on version control with Git/GitHub to maintain traceability of changes. |
| 2. Work Plan Monitoring |
| Carefully review your work plan, focusing especially on the progress status and adjustments column. |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Owner | Observations | Progress status | Adjustments |
| Software project management: scope definition, objectives, and team organization. | Project Charter | Institutional templates, team meetings. | 1 day (Aug 10 to Aug 10) | Cristóbal Rivero | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software project management: scope definition, objectives, and team organization. | Charter approval | Institutional templates, team meetings. | 2 days (Aug 10 to Aug 11) | Cristóbal Rivero | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software project management: scope definition, objectives, and team organization. | Definition of general requirements | Institutional templates, team meetings. | 6 days (Aug 12 to Aug 17) | Cristóbal Rivero | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software project management: scope definition, objectives, and team organization. | Team organization | Institutional templates, team meetings. | 5 days (Aug 17 to Aug 21) | Cristóbal Rivero | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Information systems analysis and design: requirements gathering, modeling, and software architecture. | Capture of specific requirements | SRS Document, Use Case template, diagramming tool, Mockups Document. | 5 days (Aug 24 to Aug 28) | Daphne Cuadra | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Information systems analysis and design: requirements gathering, modeling, and software architecture. | SW Architecture Document | SRS Document, Use Case template, diagramming tool, Mockups Document. | 6 days (Aug 28 to Sep 2) | Daphne Cuadra | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Information systems analysis and design: requirements gathering, modeling, and software architecture. | Use Case Document | SRS Document, Use Case template, diagramming tool, Mockups Document. | 6 days (Aug 26 to Aug 31) | Daphne Cuadra | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Information systems analysis and design: requirements gathering, modeling, and software architecture. | Prototypes | SRS Document, Use Case template, diagramming tool, Mockups Document. | 4 days (Sep 1 to Sep 4) | Daphne Cuadra | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Information systems analysis and design: requirements gathering, modeling, and software architecture. | SRS Proposal | SRS Document, Use Case template, diagramming tool, Mockups Document. | 8 days (Sep 4 to Sep 11) | Daphne Cuadra | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software development: technical implementation and database design. | Development environment setup | Supabase (PostgreSQL), SQL scripts, Git/GitHub. | 2 days (Sep 14 to Sep 15) | Daphne Cuadra | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software development: technical implementation and database design. | Creation of database table scripts | Supabase (PostgreSQL), SQL scripts, Git/GitHub. | 4 days (Sep 15 to Sep 18) | Geraldine Inostroza | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software development: technical implementation and database design. | Creation of PL/SQL query scripts | Supabase (PostgreSQL), SQL scripts, Git/GitHub. | 4 days (Sep 18 to Sep 21) | Geraldine Inostroza | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Institutional authentication and login | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 5 days (Sep 21 to Sep 25) | Daphne Cuadra | No significant difficulties; activity carried out as planned. | Completed | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Registration, roles, and profile management | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 5 days (Sep 25 to Sep 29) | Daphne Cuadra | In progress, within the timeframe defined in the Gantt Chart. | In progress | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | CRUD and classification of activities by category | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 4 days (Sep 29 to Oct 2) | Daphne Cuadra | In progress, within the timeframe defined in the Gantt Chart. | In progress | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Publishing and management of activity statuses | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 4 days (Oct 2 to Oct 5) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Enrollment and validation of slots/requirements | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 5 days (Oct 5 to Oct 9) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Attendance registration and validation | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 5 days (Oct 9 to Oct 13) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Automatic points assignment and lookup | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 4 days (Oct 13 to Oct 16) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Rewards catalog and stock management | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 4 days (Oct 16 to Oct 19) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Redemption, pickup code, and reward delivery | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 5 days (Oct 19 to Oct 23) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Automatic email notifications | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 5 days (Oct 23 to Oct 27) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Low-stock reminders and alerts | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 3 days (Oct 27 to Oct 29) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Achievement badges and activity recommendations | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 5 days (Oct 29 to Nov 2) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | Generation of filterable reports | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 3 days (Nov 2 to Nov 4) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software development: implementation of functional modules according to the defined architecture. | PDF/XLS export and activity evaluation | Ionic + Angular, Node.js, REST APIs, Git/GitHub. | 3 days (Nov 4 to Nov 6) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software quality assurance: functional verification and user validation. | Test environment setup | Test cases, testing environment, pilot users. | 2 days (Nov 9 to Nov 10) | Felipe Vega (QA) | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software quality assurance: functional verification and user validation. | Functional Testing | Test cases, testing environment, pilot users. | 15 days (Nov 10 to Nov 24) | Felipe Vega (QA) | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software quality assurance: functional verification and user validation. | User Testing | Test cases, testing environment, pilot users. | 9 days (Nov 24 to Dec 2) | Felipe Vega (QA) | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software project management: production deployment, transfer, and formal closure. | System migration to production | Production server, manuals, training materials. | 3 days (Dec 3 to Dec 5) | Geraldine Inostroza | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software project management: production deployment, transfer, and formal closure. | Training sessions | Production server, manuals, training materials. | 5 days (Dec 5 to Dec 9) | Cristóbal Rivero | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software project management: production deployment, transfer, and formal closure. | User Manuals | Production server, manuals, training materials. | 6 days (Dec 5 to Dec 10) | Daphne Cuadra | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |
| Software project management: production deployment, transfer, and formal closure. | Project closure record | Production server, manuals, training materials. | 4 days (Dec 10 to Dec 13) | Cristóbal Rivero | No observations; its scheduled start date has not yet arrived. | Not started | No adjustments |

3. Adjustments Based on Monitoring

Reflect in depth on your work plan observations. Analyze the planned activities and indicate which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, indicate the adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the development of my work plan: What has most facilitated progress has been having a Gantt Chart with clearly defined dates and owners for each activity, along with well-differentiated roles within the team (Project Manager, Developer/Designer Analyst, DBA, and QA). What most hindered development was the volume of documentation required in the Analysis and Design Phase (especially the complete SAD with its diagrams), which demanded more effort than planned. To address this, the team prioritized closing out all critical documentation before starting development, which allowed the team to enter the Development Phase without carrying over pending items.

Adjusted or eliminated activities: No activity in the work plan has been eliminated or adjusted. All tasks have been carried out as originally defined in the Gantt Chart, which was possible thanks to the clarity of the assigned roles and the fact that the documentation from the previous phase (architecture and mockups) was fully closed out before implementation began, avoiding rework.

Activities you have not started or that are delayed: As of the date of this report (September 29, 2026), no delays are recorded: all activities in the Planning and Analysis & Design phases are completed on time. The "Registration, roles, and profile management" activity is on its last scheduled day, and the Activity Management module (activities CRUD) is just starting today as planned. The remaining modules (Attendance and Points, Rewards and Redemptions, Reports and Notifications) and the Testing/QA and Implementation & Closure phases have not yet started because their scheduled start dates have not yet arrived.

If the APT Project is a group project, this column must indicate the name of the person responsible for each task or activity. This will later make it possible to differentiate the grading for each team member.